## 1. Product Overview
Category | Details
Product Name | MeetScribe AI
Product Vision / Purpose | MeetScribe AI quietly sits in your browser during virtual meetings, transcribing everything in real-time. It automatically extracts action items, analyzes speaker tone, and hands you a clean, structured summary the moment the call ends—solving the problem of forgotten verbal decisions and manual tracking.
Business Goals / Key Success Factors | • User Saving Time: Save at least 10 minutes per meeting for 80% of active users. • Accuracy / Performance: Achieve >= 95% transcription accuracy and correctly capture at least 80% of action items. • Privacy First: 100% local processing where no audio is stored permanently, building high user trust. • Scalability: Seamless integration across major platforms (Google Meet, Zoom, MS Teams web). • Innovation: Multi-model AI approach combining HuggingFace for audio and Gemini 1.5 Flash for conversational intelligence.
Primary Stakeholders | • End Users: Team leads, project managers, and virtual meeting professionals. • Developers: Chrome Extension maintainers and AI/API integration engineers. • Admin: IT Admins / Workspace Managers deploying productivity tools. • External partners: API Providers (Google Gemini API, HuggingFace Inference).

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirement | Priority (MoSCoW) | Story Point | Status | Owner | Test Case (Tasks) | Test Owner
| Major features | Mandatory | Mandatory | Mandatory | (optional) | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory
E1 | Real-Time Audio Capture & Transcription | US1 | As a user, I want the extension to capture my meeting audio directly from the browser tab so that I don't need secondary recording software. | Implement audio buffer chunking in the offscreen document. | Must Have | 5 | To Do | Backend Dev | Trigger extension on Google Meet and verify audio state is successfully captured without echoing. | QA Team
E1 | Real-Time Audio Capture & Transcription | US2 | As a user, I want my speech transcribed in real-time so that I can see the meeting notes happening live. | Integrate HuggingFace Whisper API. | Must Have | 8 | To Do | Backend Dev | Speak a test phrase and verify text populates. | QA Team
E2 | AI Insights & Action Item Extraction | US3 | As a project manager, I want the AI to automatically extract action items so that I don't have to manually update JIRA/Trello later. | Prompt Gemini 1.5 to return JSON tasks. | Must Have | 5 | In Progress | Frontend Dev | Verify Gemini outputs JSON action objects. | QA Team
E2 | AI Insights & Action Item Extraction | US4 | As a team lead, I want to analyze the tone/sentiment of the meeting to gauge team confidence and energy. | Implement Speaker Diarization logic. | Could Have | 3 | To Do | Frontend Dev | Verify sentiment tags render in UI. | QA Team
E3 | Extension UI & Data Export | US5 | As a user, I want the tool docked as a sleek sidebar so that my primary meeting view is unobstructed. | Develop Content Script for React UI. | Must Have | 3 | To Do | Frontend Dev | Toggle extension and ensure layout responsiveness. | QA Team
E3 | Extension UI & Data Export | US6 | As a user, I want to export my transcripts in multiple formats so that I can store them in my personal knowledge base. | Create blob generation logic for exports. | Should Have | 2 | To Do | Backend Dev | Click 'Export' and verify downloaded file. | QA Team
Notes: | MoSCoW
|  | Must Have | Critical requirements that are essential for the project's success and must be delivered.
|  | Should Have | Important requirements that are highly desirable but not vital; the project can still be delivered without them.
|  | Could Have | 'Nice-to-have' requirements that are less important and have a lower impact if they are not included.
|  | Won't Have | Requirements that are not being delivered in the current project or timeframe, but may be considered for future iterations.
Story Points
|  | Fibonacci | 0,1,1,2,3,5,8,13,21,34...
|  | (Modified) | 0,1,1,2,3,5,8,13,20 (points decided based on a User Story's complexity, effort needed & risks)

## 3. Product Roadmap
Release | Date | Key Features | Dependencies | Demo Status
List Epic Names
v0.1 | Week 1 | Basic setup (Sidebar UI, API boilerplate) | None | On Track
v0.2 | Week 2 | E1: Tab Audio Capture & Basic Offscreen | Browser APIs | On Track
v0.3 | Week 3 | E1: Whisper API integration | HuggingFace Token | Planned
v0.4 | Week 4 | E2: AI Insights & Tone Analysis | Gemini API Key | Planned
v0.5 | Week 5 | E3: Speaker diarization, Export features | Transcript Data | Yet to Plan
v1.0 | Week 6 | Final product: UI polish, bug fixes | All above | Yet to Plan

## 4. Retrospective
What Went Well | What Didn't Go Well | Improvements / Action Items | Owner
Next time what will you do differently
Team collaboration and repository structuring was great. | Handling Manifest V3 offscreen document message passing. | Automate test pipeline in next sprint. | Test Lead
Fast frontend-backend integration completion. | Network latency with external inference APIs. | Transition to WebLLM for local inference. | Dev Lead